## Sheet1
Sr. no | Work | Remarks | Review date 02/11/2018 | Target Date | Responsible Person | Status |  | Umesh
1 | Ammonia Sensor | Quotation given PO pending | PO sent, delivery date 15/08/2018 | 2018-08-16 | Yogesh | Completed |  | Uttam
2 | Cl2 sensor | Quotation given PO pending | Completed for exsting, for new same as above |  | Yogesh | Completed |  | Yogesh
3 | New ammonia sensor with transmitter | TBE given to Jayesh | CEP Ready for HO | 2018-07-30 | Vaishnabi | Pending |  | Mitul
4 | ACP pH sensor | PO given |  |  | Vaishnabi | Completed |  | Vaishnabi
5 | cl2 mass flowmeter | waiting for offer | Negotiation going on | 2018-10-31 | Yogesh | Pending |  | Chirag
6 | cl2 rota transmiter |  |  |  | Yogesh | Completed |  | Jitendra
7 | pcl3 rota transmiter | Trial pending, process issue | Process clearence not given | 2018-08-25 | Yogesh | Pending | Process clearence not given | Satish
8 | mnso4 dbh pump |  |  |  | Uttam | Completed
9 | TMP 20kl aquas tank LI | PR Raised | Material received | 2018-08-25 | Uttam | Pending
10 | tmp hcl LI | PR Raised | Tobe check | 2018-08-15 | Uttam | Pending
11 | utility spare | PR Raised | Some material received & installed | 2018-08-25 | Yogesh | Pending
12 | Boiler TDS meter | PO send to vendor, delivery 11/07 | New TDS meter to b eprocure | 2017-07-28 | Satish | Pending
13 | Boiler O2 analyser | PO pending | PO sent , waiting for material | 2018-08-25 | Yogesh | Completed
14 | 130 TR scaner mounting |  |  | 2018-09-30 | Yogesh | Pending
15 | MEE PLC/HMI | Offer given to Jayesh | PO waiting | 2018-08-30 | Umesh | Completed
16 | MEE-4 steam flowmeter |  |  |  | Umesh | Completed
17 | ANF mag Flowmeter |  | Line modification pending | 2018-08-16 | Umesh | Completed
18 | silo weight indicator |  | To be check |  | Umesh | Completed
19 | PNB multiblock |  | Material received |  | Umesh | Completed
20 | all module follow up |  |  |  | Uttam | Completed
21 | ETP DO meter |  | Material received | 2018-10-25 | Vaishnabi | Pending
22 | ETP all inst calibration |  |  |  | Umesh | Completed
23 | TOC/CEMS all parameter in DCS |  | TOC is in line only inc-1 CEMS pending | 2017-07-28 | Uttam | Completed
24 | Acp steam flowmeter |  |  |  | Umesh | Completed
25 | MNZ B 6 nos pump pending |  |  |  | Uttam | Completed
26 | GLP PTS valve (Aira) |  | PO pending |  | Yogesh | Completed
27 | MPP UPS/CEMS ups |  |  |  | Uttam | Completed
28 | PA system(CEP) |  | CEP to be made |  | Yogesh | Pending
29 | weigh mark payment |  |  |  | Umesh | Completed
30 | servo motor | PO pending |  |  | Vaishnabi | Completed
31 | IR compressor PLC |  | To be check the material |  | Umesh | Pending
32 | mnso4 radar |  |  |  | Uttam | Completed
33 | pcl3 radar |  | Management dissision pending |  | Jitendra | Pending
34 | RVDF cylinder load cell |  | Material received | 2018-10-10 | Vaishnabi | Pending
35 | RVDF cylinder(tracking device) |  | PR raised | 2018-09-30 | Umesh | Pending
36 | multimeter |  |  |  | Umesh | Completed
37 | libra CL2 shed | Service Po |  |  | Vaishnabi | Completed
38 | Stamping PO |  | PO pending | 2018-08-14 | Yogesh | Completed
39 | FAS service |  | to be check |  | Yogesh | Pending
40 | 10000 tag updation |  | shutdown plan |  | Uttam | Completed
41 | MNZA 30meter panel |  | Material will be received on 20th nov. |  | Umesh | Pending
42 | 30kva ups scrap |  | Sales order is pending at Mr. Boopati |  | Jitendra | Pending
43 | New Points on dated 28/06/18
44 | CS2 sensor fail |  |  |  | Umesh | completed
45 | FAS repeater panel procured new as old is damaged |  | PR raised | 2018-08-25 | Yogesh | completed
46 | MEE 4 Annunciator panel issue |  | PR raised | 2018-08-25 | Umesh | completed
47 | MNZ-A Hot water valve problem |  | PO pending | 2018-09-25 | Umesh | completed
48 | MCP Auto drum system service required |  |  |  | Yogesh | completed
49 | MCP Chlorination tonner WS indicator to be procure |  |  | 2018-08-25 | Yogesh | completed
New Points on dated 25/07/18
50 | ETP clarifier Ph meter |  | PO sent |  | Mitul | Pending
51 | MECL flow meter to be rectify |  |  |  | Chirag | canceled
52 | Feed back assembly for XV to be procure |  |  |  | Uttam | completed
53 | New TOC analyser to be procure |  | CEP sent to HO |  | Jitendra | Pending
54 | C9 LI to be repaire |  |  |  | Yogesh | Pending
55 | ACP LP stem flow meter |  |  |  | Yogesh | completed
56 | GLP LP steam flow meter |  |  |  | Uttam | completed
57 | MNZ-B LP Steam flow meter |  | To be check |  | Vaishnabi | Pending
58 | Dil. EDA tank float issue |  |  |  | Umesh | completed
59 | GLP PRV issue |  | PO Sent |  | Yogesh | Pending
60 | TMP NH3 control valve(New) issue |  | TBE pending |  | Umesh | Pending
61 | TMP distilation column reboiler CV problem |  | New to procure |  | Yogesh | Pending
62 | MEE 5 condensate CV issue |  |  |  | Umesh | completed
63 | MNZ-A Pindmill VFD |  |  |  | umesh | completed
64 | Telephone provide for new cabin |  |  |  | Yogesh | completed
65 | Provide FLP telephone for Hazardous area |  |  |  | Mitul | Pending
66 | All JB should be properly close |  |  |  | Uttam | Pending
67 | DBH CEMS connectivity issue |  | discussed with vendor for board replacement |  | Umesh | Pending
68 | Hot line to be provide for 333 & 666 |  |  | 2018-07-28 | Yogesh | completed
New Points on dated 02/11/18
69 | MNSO4 control valve to be replaced(MNZ-B) |  |  |  | Uttam | Pending
70 | FAS control panel to be replace |  |  |  | Yogesh | Pending
71 | CS2 sensor fail plant side |  |  |  | Umesh | completed
72 | MEE cond. Water pit LS |  |  |  | Mitul | Pending
73 | MEE-5 PLC replacement |  |  |  | Uttam | Pending
74 | Auto repot not generate in TMP,EDA,DBH-B |  |  |  | Uttam | Pending
75 | Kirloskar chiller card issue |  |  |  | Yogesh | Pending
76 | MNZ-B N2 plant PLC to be repaire |  |  |  | Yogesh | Pending
77 | ETP outlet PH sensor to be replace |  |  |  | Umesh | Pending